## Sheet1
project | constant_load | wp | activity | staff | num_days | start_date | deadline | progress | cost
PPI | FALSE | Planning | Latent Class Analysis | Amir | 15 | 2024-05-27 | 2024-07-30 | 0 | 12540
PPI | FALSE | Planning | Update PPI | Amir | 10 | 2024-08-01 | 2024-08-30 | 0 | 8360
PPI | FALSE | Planning | Update Charts | Nathan | 10 | 2024-09-01 | 2024-09-30 | 0 | 3000
PPI | FALSE | Development | Writing | Amir | 15 | 2024-10-01 | 2024-10-30 | 0 | 12540
PPI | FALSE | Development | Writing | Nathan | 15 | 2024-10-01 | 2024-10-30 | 0 | 4500
PPI | FALSE | Execution | Proofreading | Mike | 10 | 2024-11-01 | 2024-11-15 | 0 | 6000
PPI | FALSE | Execution | Layout | Wallace | 15 | 2024-11-15 | 2024-11-30 | 0 | 7500
PPI | TRUE | Project Management | Project Management | Amir | 54 | 2024-05-24 | 2024-12-01 | 0
P4P FY24 | FALSE | Planning | Data Audit + Indicator List | Briahna | 5 | 2024-05-28 | 2024-06-11 | 0 | 3000
P4P FY24 | FALSE | Development | Draft Index | Briahna | 2 | 2024-06-11 | 2024-06-30 | 0 | 1200
P4P FY24 | FALSE | Development | Final Index + Methodology | Briahna | 10 | 2024-06-30 | 2024-07-15 | 0 | 6000
P4P FY24 | FALSE | Development | Support | David | 10 | 2024-06-11 | 2024-07-15 | 0 | 10000
P4P FY24 | FALSE | Execution | Writing | Briahna | 20 | 2024-08-01 | 2024-09-30 | 0 | 12000
P4P FY24 | FALSE | Execution | Writing | Niharika | 20 | 2024-08-01 | 2024-09-30 | 0 | 16720
P4P FY24 | TRUE | Project Management | Project Management | Briahna | 30 | 2024-06-05 | 2024-12-31 | 0
Water and Peace FY24 | FALSE | Planning | Literature Review | Paulina | 5 | 2024-06-15 | 2024-08-15 | 0 | 3000
Water and Peace FY24 | FALSE | Planning | Literature Review | Sascha | 3 | 2024-06-15 | 2024-08-15 | 0 | 2508
Water and Peace FY24 | FALSE | Planning | Modelling Review | Amir | 10 | 2024-06-15 | 2024-08-15 | 0 | 8360
Water and Peace FY24 | FALSE | Development | Methodology Development | Amir | 10 | 2024-08-15 | 2024-09-30 | 0 | 8360
Water and Peace FY24 | FALSE | Development | Framework Development | Sascha | 5 | 2024-08-15 | 2024-09-30 | 0 | 4180
Water and Peace FY24 | FALSE | Development | Framework Development | Paulina | 5 | 2024-08-15 | 2024-09-30 | 0 | 3000
Water and Peace FY24 | FALSE | Execution | Writing Framework | Paulina | 5 | 2024-10-01 | 2024-12-31 | 0 | 3000
Water and Peace FY24 | FALSE | Execution | Writing Methodology | Amir | 10 | 2024-10-01 | 2024-12-31 | 0 | 8360
Water and Peace FY24 | FALSE | Execution | Writing Framework | Sascha | 10 | 2024-10-01 | 2024-12-31 | 0 | 8360
Water and Peace FY24 | TRUE | Project Management | Project Management | David | 14.5 | 2024-06-10 | 2024-12-31 | 0
Country Reports FY24 | FALSE | Planning | Wireframes | David | 5 | 2024-05-22 | 2024-06-20 | 0 | 5000
Country Reports FY24 | FALSE | Planning | Work through process with Comms | Karan | 5 | 2024-05-22 | 2024-06-20 | 0 | 3000
Country Reports FY24 | FALSE | Development | Set up R Scripts | Karan | 20 | 2024-06-20 | 2024-09-30 | 0 | 12000
Country Reports FY24 | FALSE | Development | Implement Process | Darren | 5 | 2024-09-01 | 2024-09-30 | 0 | 5000
Country Reports FY24 | FALSE | Execution | Testing and validation | Karan | 10 | 2024-09-30 | 2024-10-15 | 0 | 6000
Country Reports FY24 | TRUE | Project Management | Project Management | David | 15 | 2024-06-05 | 2024-12-31 | 0
AI Processes | FALSE | Execution | Execute | Thom | 20 | 2024-05-22 | 2024-09-30 | 0 | 18000
GPSI FY24 | FALSE | Planning | Data Audit + Indicator List | Briahna | 5 | 2024-05-22 | 2024-06-01 | 0 | 3000
GPSI FY24 | FALSE | Planning | Updated Index | Briahna | 2 | 2024-06-01 | 2024-06-15 | 0 | 1200
GPSI FY24 | FALSE | Planning | Final Index + Methodology | Briahna | 5 | 2024-06-15 | 2024-08-30 | 0 | 3000
GPSI FY24 | FALSE | Planning | Learn how to manage website | Briahna | 5 | 2024-05-22 | 2024-06-30 | 0 | 3000
GPSI FY24 | FALSE | Planning | Develop Police Network | Niharika | 10 | 2024-05-22 | 2024-06-30 | 0 | 8360
GPSI FY24 | FALSE | Planning | Generate 2 blogs from existing report | Nathan | 10 | 2024-05-22 | 2024-06-30 | 0 | 3000
GPSI FY24 | FALSE | Development | Upload Data and Articles to Website | Briahna | 10 | 2024-08-30 | 2024-10-15 | 0 | 6000
GPSI FY24 | FALSE | Development | Research CoE | Niharika | 10 | 2024-05-22 | 2024-07-31 | 0 | 8360
GPSI FY24 | FALSE | Development | Draft CoE Proposal | Niharika | 10 | 2024-08-01 | 2024-08-15 | 0 | 8360
GPSI FY24 | FALSE | Development | Organise Workshop | Niharika | 10 | 2024-08-16 | 2024-09-15 | 0 | 8360
GPSI FY24 | FALSE | Development | Execute Workshop | Niharika | 5 | 2024-09-15 | 2024-09-20 | 0 | 4180
GPSI FY24 | FALSE | Execution | Final CoE Proposal | Niharika | 10 | 2024-09-15 | 2024-11-30 | 0 | 8360
GPSI FY24 | FALSE | Execution | Website Testing | Briahna | 20 | 2024-09-01 | 2024-10-15 | 0 | 12000
GPSI FY24 | TRUE | Project Management | Project Management | Niharika | 30 | 2024-06-05 | 2024-12-31 | 0
kaduna | FALSE | Planning | Data Audit | Paulina | 4 | 2024-05-22 | 2024-05-28 | 0 | 2400
kaduna | FALSE | Development | Analysis | Paulina | 7 | 2024-05-28 | 2024-06-07 | 0 | 4200
kaduna | FALSE | Development | Writing | Paulina | 7 | 2024-06-03 | 2024-06-14 | 0 | 4200
kaduna | TRUE | Project Management | Project Management | Alex | 15 | 2024-06-05 | 2024-07-15 | 0
ETR | FALSE | Preliminary Work | Focus Section Scoping | Sascha | 26 | 2024-05-27 | 2024-07-01 | 0 | 21736
ETR | FALSE | Preliminary Work | Focus Section Writing | Sascha | 19 | 2024-07-02 | 2024-07-26 | 0 | 15884
ETR | FALSE | Data Tasks | Index Methodology Review | David | 10 | 2024-06-24 | 2024-07-05 | 0 | 10000
ETR | FALSE | Data Tasks | New Index Calculation | David | 15 | 2024-07-08 | 2024-07-26 | 0 | 15000
ETR | FALSE | Data Tasks | Update ETR Repository | Thom | 10 | 2024-07-08 | 2024-07-20 | 0 | 9000
ETR | FALSE | Data Tasks | ETR Dashboard | Thom | 5 | 2024-07-21 | 2024-07-26 | 0 | 4500
ETR | FALSE | Report Tasks | Results | Karan | 6 | 2024-07-29 | 2024-08-05 | 0 | 3600
ETR | FALSE | Report Tasks | Hotspots | Sascha | 5 | 2024-08-06 | 2024-08-16 | 0 | 4180
ETR | FALSE | Report Tasks | Indicator Sections | Karan | 6 | 2024-07-29 | 2024-08-05 | 0 | 3600
ETR | FALSE | Report Tasks | Policy Recommendations | Sascha | 9 | 2024-08-06 | 2024-08-16 | 0 | 7524
ETR | FALSE | Report Tasks | Appendices | Thom | 2 | 2024-07-29 | 2024-07-30 | 0 | 1800
ETR | FALSE | Layout and Collateral | Powerpoint | Darren | 3 | 2024-09-04 | 2024-09-07 | 0 | 3000
ETR | FALSE | Layout and Collateral | Web data | Thom | 2 | 2024-09-02 | 2024-09-03 | 0 | 1800
ETR | FALSE | Layout and Collateral | Press Release | Darren | 4 | 2024-09-08 | 2024-09-12 | 0 | 4000
ETR | FALSE | Layout and Collateral | Layout, PDF checking | Wallace | 13 | 2024-09-02 | 2024-09-18 | 0 | 6500
ETR | TRUE | Project Management | Project Management | Alex | 48 | 2024-06-05 | 2024-09-25 | 0
CIVIC | FALSE | Development | Index Calculation | Amir | 5 | 2024-05-27 | 2024-05-31 | 0 | 4180
CIVIC | FALSE | Development | Identify Secondary Data Areas | Thom | 2 | 2024-05-27 | 2024-05-28 | 0 | 1800
CIVIC | FALSE | Development | Write-up Index Results | Thom | 3 | 2024-05-29 | 2024-05-31 | 0 | 2700
CIVIC | FALSE | Development | Meet with Civic | Thom | 1 | 2024-06-03 | 2024-06-04 | 0 | 900
CIVIC | FALSE | Development | Refine Index | Amir | 4 | 2024-06-04 | 2024-06-07 | 0 | 3344
CIVIC | TRUE | Project Management | Project Management | Thom | 3 | 2024-06-05 | 2024-07-15 | 0
GPI | FALSE | Layout and Collateral | Web Data and Collateral | Thom | 1 | 2024-05-27 | 2024-05-27 | 0 | 900
GPI | FALSE | Layout and Collateral | Powerpoint Draft | Thom | 3 | 2024-05-27 | 2024-05-29 | 0 | 2700
GPI | FALSE | Layout and Collateral | Powerpoint Final | Darren | 3 | 2024-05-29 | 2024-06-02 | 0 | 3000
GPI | FALSE | Layout and Collateral | Layout | Wallace | 6 | 2024-05-25 | 2024-06-03 | 0 | 3000
GPI | FALSE | Layout and Collateral | Section Checking | Mike | 6 | 2024-05-27 | 2024-06-03 | 0 | 3600
GPI | FALSE | Layout and Collateral | Press Release | Darren | 5 | 2024-05-27 | 2024-05-31 | 0 | 5000
GPI | FALSE | Layout and Collateral | Miscellaneous Checking, PR | Thom | 2 | 2024-05-30 | 2024-05-31 | 0 | 1800
GPI | FALSE | Launch and Follow Up | Launch Event | Thom | 1 | 2024-06-11 | 2024-06-11 | 0 | 900
GPI | FALSE | Launch and Follow Up | Interviews | Thom | 3 | 2024-06-12 | 2024-06-14 | 0 | 2700
Management | TRUE | Execution | Admin and Mgmt | David | 30 | 2024-05-22 | 2024-12-31 | 0 | 30000
Management | TRUE | Execution | Pipeline | David | 60 | 2024-05-22 | 2024-12-31 | 0 | 60000
Management | TRUE | Execution | Pipeline | Niharika | 90 | 2024-05-22 | 2024-12-31 | 0 | 75240
Management | TRUE | Execution | Pipeline | Karan | 60 | 2024-05-22 | 2024-12-31 | 0 | 36000
Leave | TRUE | Leave | Leave | Niharika | 20 | 2024-09-30 | 2024-10-25 | 0 | 16720
PPI | FALSE | Planning | Latent Class Analysis | Amir | 15 | 2024-05-27 | 2024-07-30 | 0 | 12540
PPI | FALSE | Planning | Update PPI | Amir | 10 | 2024-08-01 | 2024-08-30 | 0 | 8360
PPI | FALSE | Planning | Update Charts | Nathan | 10 | 2024-09-01 | 2024-09-30 | 0 | 3000
PPI | FALSE | Development | Writing | Amir | 15 | 2024-10-01 | 2024-10-30 | 0 | 12540
PPI | FALSE | Development | Writing | Nathan | 15 | 2024-10-01 | 2024-10-30 | 0 | 4500
PPI | FALSE | Execution | Proofreading | Mike | 10 | 2024-11-01 | 2024-11-15 | 0 | 6000
PPI | FALSE | Execution | Layout | Wallace | 15 | 2024-11-15 | 2024-11-30 | 0 | 7500
PPI | TRUE | Project Management | Project Management | Amir | 54 | 2024-05-24 | 2024-12-01 | 0
P4P FY24 | FALSE | Planning | Data Audit + Indicator List | Briahna | 5 | 2024-05-28 | 2024-06-11 | 0 | 3000
P4P FY24 | FALSE | Development | Draft Index | Briahna | 2 | 2024-06-11 | 2024-06-30 | 0 | 1200
P4P FY24 | FALSE | Development | Final Index + Methodology | Briahna | 10 | 2024-06-30 | 2024-07-15 | 0 | 6000
P4P FY24 | FALSE | Development | Support | David | 10 | 2024-06-11 | 2024-07-15 | 0 | 10000
P4P FY24 | FALSE | Execution | Writing | Briahna | 20 | 2024-08-01 | 2024-09-30 | 0 | 12000
P4P FY24 | FALSE | Execution | Writing | Niharika | 20 | 2024-08-01 | 2024-09-30 | 0 | 16720
P4P FY24 | TRUE | Project Management | Project Management | Briahna | 30 | 2024-06-05 | 2024-12-31 | 0
Water and Peace FY24 | FALSE | Planning | Literature Review | Paulina | 5 | 2024-06-15 | 2024-08-15 | 0 | 3000
Water and Peace FY24 | FALSE | Planning | Literature Review | Sascha | 3 | 2024-06-15 | 2024-08-15 | 0 | 2508
Water and Peace FY24 | FALSE | Planning | Modelling Review | Amir | 10 | 2024-06-15 | 2024-08-15 | 0 | 8360
Water and Peace FY24 | FALSE | Development | Methodology Development | Amir | 10 | 2024-08-15 | 2024-09-30 | 0 | 8360
Water and Peace FY24 | FALSE | Development | Framework Development | Sascha | 5 | 2024-08-15 | 2024-09-30 | 0 | 4180
Water and Peace FY24 | FALSE | Development | Framework Development | Paulina | 5 | 2024-08-15 | 2024-09-30 | 0 | 3000
Water and Peace FY24 | FALSE | Execution | Writing Framework | Paulina | 5 | 2024-10-01 | 2024-12-31 | 0 | 3000
Water and Peace FY24 | FALSE | Execution | Writing Methodology | Amir | 10 | 2024-10-01 | 2024-12-31 | 0 | 8360
Water and Peace FY24 | FALSE | Execution | Writing Framework | Sascha | 10 | 2024-10-01 | 2024-12-31 | 0 | 8360
Water and Peace FY24 | TRUE | Project Management | Project Management | David | 14.5 | 2024-06-10 | 2024-12-31 | 0
Country Reports FY24 | FALSE | Planning | Wireframes | David | 5 | 2024-05-22 | 2024-06-20 | 0 | 5000
Country Reports FY24 | FALSE | Planning | Work through process with Comms | Karan | 5 | 2024-05-22 | 2024-06-20 | 0 | 3000
Country Reports FY24 | FALSE | Development | Set up R Scripts | Karan | 20 | 2024-06-20 | 2024-09-30 | 0 | 12000
Country Reports FY24 | FALSE | Development | Implement Process | Darren | 5 | 2024-09-01 | 2024-09-30 | 0 | 5000
Country Reports FY24 | FALSE | Execution | Testing and validation | Karan | 10 | 2024-09-30 | 2024-10-15 | 0 | 6000
Country Reports FY24 | TRUE | Project Management | Project Management | David | 15 | 2024-06-05 | 2024-12-31 | 0
AI Processes | FALSE | Execution | Execute | Thom | 20 | 2024-05-22 | 2024-09-30 | 0 | 18000
GPSI FY24 | FALSE | Planning | Data Audit + Indicator List | Briahna | 5 | 2024-05-22 | 2024-06-01 | 0 | 3000
GPSI FY24 | FALSE | Planning | Updated Index | Briahna | 2 | 2024-06-01 | 2024-06-15 | 0 | 1200
GPSI FY24 | FALSE | Planning | Final Index + Methodology | Briahna | 5 | 2024-06-15 | 2024-08-30 | 0 | 3000
GPSI FY24 | FALSE | Planning | Learn how to manage website | Briahna | 5 | 2024-05-22 | 2024-06-30 | 0 | 3000
GPSI FY24 | FALSE | Planning | Develop Police Network | Niharika | 10 | 2024-05-22 | 2024-06-30 | 0 | 8360
GPSI FY24 | FALSE | Planning | Generate 2 blogs from existing report | Nathan | 10 | 2024-05-22 | 2024-06-30 | 0 | 3000
GPSI FY24 | FALSE | Development | Upload Data and Articles to Website | Briahna | 10 | 2024-08-30 | 2024-10-15 | 0 | 6000
GPSI FY24 | FALSE | Development | Research CoE | Niharika | 10 | 2024-05-22 | 2024-07-31 | 0 | 8360
GPSI FY24 | FALSE | Development | Draft CoE Proposal | Niharika | 10 | 2024-08-01 | 2024-08-15 | 0 | 8360
GPSI FY24 | FALSE | Development | Organise Workshop | Niharika | 10 | 2024-08-16 | 2024-09-15 | 0 | 8360
GPSI FY24 | FALSE | Development | Execute Workshop | Niharika | 5 | 2024-09-15 | 2024-09-20 | 0 | 4180
GPSI FY24 | FALSE | Execution | Final CoE Proposal | Niharika | 10 | 2024-09-15 | 2024-11-30 | 0 | 8360
GPSI FY24 | FALSE | Execution | Website Testing | Briahna | 20 | 2024-09-01 | 2024-10-15 | 0 | 12000
GPSI FY24 | TRUE | Project Management | Project Management | Niharika | 30 | 2024-06-05 | 2024-12-31 | 0
kaduna | FALSE | Planning | Data Audit | Paulina | 4 | 2024-05-22 | 2024-05-28 | 0 | 2400
kaduna | FALSE | Development | Analysis | Paulina | 7 | 2024-05-28 | 2024-06-07 | 0 | 4200
kaduna | FALSE | Development | Writing | Paulina | 7 | 2024-06-03 | 2024-06-14 | 0 | 4200
kaduna | TRUE | Project Management | Project Management | Alex | 15 | 2024-06-05 | 2024-07-15 | 0
ETR | FALSE | Preliminary Work | Focus Section Scoping | Sascha | 26 | 2024-05-27 | 2024-07-01 | 0 | 21736
ETR | FALSE | Preliminary Work | Focus Section Writing | Sascha | 19 | 2024-07-02 | 2024-07-26 | 0 | 15884
ETR | FALSE | Data Tasks | Index Methodology Review | David | 10 | 2024-06-24 | 2024-07-05 | 0 | 10000
ETR | FALSE | Data Tasks | New Index Calculation | David | 15 | 2024-07-08 | 2024-07-26 | 0 | 15000
ETR | FALSE | Data Tasks | Update ETR Repository | Thom | 10 | 2024-07-08 | 2024-07-20 | 0 | 9000
ETR | FALSE | Data Tasks | ETR Dashboard | Thom | 5 | 2024-07-21 | 2024-07-26 | 0 | 4500
ETR | FALSE | Report Tasks | Results | Karan | 6 | 2024-07-29 | 2024-08-05 | 0 | 3600
ETR | FALSE | Report Tasks | Hotspots | Sascha | 5 | 2024-08-06 | 2024-08-16 | 0 | 4180
ETR | FALSE | Report Tasks | Indicator Sections | Karan | 6 | 2024-07-29 | 2024-08-05 | 0 | 3600
ETR | FALSE | Report Tasks | Policy Recommendations | Sascha | 9 | 2024-08-06 | 2024-08-16 | 0 | 7524
ETR | FALSE | Report Tasks | Appendices | Thom | 2 | 2024-07-29 | 2024-07-30 | 0 | 1800
ETR | FALSE | Layout and Collateral | Powerpoint | Darren | 3 | 2024-09-04 | 2024-09-07 | 0 | 3000
ETR | FALSE | Layout and Collateral | Web data | Thom | 2 | 2024-09-02 | 2024-09-03 | 0 | 1800
ETR | FALSE | Layout and Collateral | Press Release | Darren | 4 | 2024-09-08 | 2024-09-12 | 0 | 4000
ETR | FALSE | Layout and Collateral | Layout, PDF checking | Wallace | 13 | 2024-09-02 | 2024-09-18 | 0 | 6500
ETR | TRUE | Project Management | Project Management | Alex | 48 | 2024-06-05 | 2024-09-25 | 0
CIVIC | FALSE | Development | Index Calculation | Amir | 5 | 2024-05-27 | 2024-05-31 | 0 | 4180
CIVIC | FALSE | Development | Identify Secondary Data Areas | Thom | 2 | 2024-05-27 | 2024-05-28 | 0 | 1800
CIVIC | FALSE | Development | Write-up Index Results | Thom | 3 | 2024-05-29 | 2024-05-31 | 0 | 2700
CIVIC | FALSE | Development | Meet with Civic | Thom | 1 | 2024-06-03 | 2024-06-04 | 0 | 900
CIVIC | FALSE | Development | Refine Index | Amir | 4 | 2024-06-04 | 2024-06-07 | 0 | 3344
CIVIC | TRUE | Project Management | Project Management | Thom | 3 | 2024-06-05 | 2024-07-15 | 0
GPI | FALSE | Layout and Collateral | Web Data and Collateral | Thom | 1 | 2024-05-27 | 2024-05-27 | 0 | 900
GPI | FALSE | Layout and Collateral | Powerpoint Draft | Thom | 3 | 2024-05-27 | 2024-05-29 | 0 | 2700
GPI | FALSE | Layout and Collateral | Powerpoint Final | Darren | 3 | 2024-05-29 | 2024-06-02 | 0 | 3000
GPI | FALSE | Layout and Collateral | Layout | Wallace | 6 | 2024-05-25 | 2024-06-03 | 0 | 3000
GPI | FALSE | Layout and Collateral | Section Checking | Mike | 6 | 2024-05-27 | 2024-06-03 | 0 | 3600
GPI | FALSE | Layout and Collateral | Press Release | Darren | 5 | 2024-05-27 | 2024-05-31 | 0 | 5000
GPI | FALSE | Layout and Collateral | Miscellaneous Checking, PR | Thom | 2 | 2024-05-30 | 2024-05-31 | 0 | 1800
GPI | FALSE | Launch and Follow Up | Launch Event | Thom | 1 | 2024-06-11 | 2024-06-11 | 0 | 900
GPI | FALSE | Launch and Follow Up | Interviews | Thom | 3 | 2024-06-12 | 2024-06-14 | 0 | 2700
Management | TRUE | Execution | Admin and Mgmt | David | 30 | 2024-05-22 | 2024-12-31 | 0 | 30000
Management | TRUE | Execution | Pipeline | David | 60 | 2024-05-22 | 2024-12-31 | 0 | 60000
Management | TRUE | Execution | Pipeline | Niharika | 90 | 2024-05-22 | 2024-12-31 | 0 | 75240
Management | TRUE | Execution | Pipeline | Karan | 60 | 2024-05-22 | 2024-12-31 | 0 | 36000
Leave | TRUE | Leave | Leave | Niharika | 20 | 2024-09-30 | 2024-10-25 | 0 | 16720